# Timeline — PlayLive Floor App

Version: v0.3 — Companion to SOW v0.4 and Action Plan v0.3 12-week Build phase: 4 May → 26 July 2026 Rollout phase (UAT, training, cutover) runs separately afterwards.

## How v0.3 differs from v0.2

- Phases 7 (UAT & Parallel Run) and 8 (Cutover) removed from the 12-week window. Now sit in a separate Rollout phase scheduled around PlayLive's tournament calendar.

- Phase 6 (Consumer-app Adaptors) moved to Week 12 as the build-phase closer.

- Wallet & withdrawal work absorbed into Phases 1, 3, and 4 — Phase 3 grew from 2 to 3 weeks; Phase 4 grew from 2 to 3 weeks.

- Offline-tolerance simulation (was Phase 5 in v0.2) is gone — Floor App is online-only.

## Build phase — Gantt (12 weeks)

Week 1 starts Mon 4 May 2026; Week 12 finishes Sun 26 July 2026.

| Phase | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0 — Discovery & Setup | ██ |  |  |  |  |  |  |  |  |  |  |  |
| 1 — Foundations |  | ██ | ██ |  |  |  |  |  |  |  |  |  |
| 2 — Tournament Setup & Clock |  |  | ██ | ██ | ██ |  |  |  |  |  |  |  |
| 3 — Registration, Seating, Wallet |  |  |  |  | ██ | ██ | ██ | ██ |  |  |  |  |
| 4 — Payouts, Results & Withdrawals |  |  |  |  |  |  |  | ██ | ██ | ██ |  |  |
| 5 — Display & iPad Polish |  |  |  |  |  |  |  |  |  | ██ | ██ |  |
| 6 — Consumer-app Adaptors |  |  |  |  |  |  |  |  |  |  |  | ██ |

## Build phase — Week-by-week

| Wk | Phase | Focus this week | Milestone / Output |
| --- | --- | --- | --- |
| 1 | Phase 0 | Casinoware feature inventory + wallet discovery (shadow registration desk). Audit existing Firestore. Stand up empty repo and staging Firebase. Lock ADR-001 (online-only). | Feature inventory, wallet design note, schema audit, staging Firebase up |
| 2 | Phase 1 | Firebase Auth + four staff roles. App shell with persona-tailored landing screens. Begin firestore.rules covering all collections including wallet collections. | Login flow working with role claims |
| 3 | Phase 1+2 | Finalise Firestore rules and deploy to staging (HARD GATE). Runtime validator module. Wallet ledger module (no UI). Begin tournament create/edit form and blind-structure builder. | Rules deployed. Schema v1 frozen. Wallet ledger primitives ready. |
| 4 | Phase 2 | Payout structure builder (with auto-generate). Satellite + multi-flight setup. Tournament templates + weekly recurring generator. Live clock engine. | Working clock prototype |
| 5 | Phase 2→3 | Floor controls (pause/resume/jump). Internal Phase 2 walk-through. Begin player search + new player registration with enhanced profile fields. | Phase 2 sign-off |
| 6 | Phase 3 | Registration with multi-method payment selection (cash, EFTPOS, PayID, wallet, ticket). Ticket equal-or-greater rule. Wallet deposit screen including PayID wizard. | Registration + all 5 payment methods live on staging |
| 7 | Phase 3 | Seat assignment + printable seat list. Table balancing engine. Table breaking. Waitlist with alternate ticket printing. | Seating + balancing + alternates working |
| 8 | Phase 3→4 | Per-player transaction ledger view. Internal Phase 3 walk-through (mock tournament with every payment method). Begin bust-out recording. | Phase 3 sign-off |
| 9 | Phase 4 | Payout calculator. Mystery Bounty draw flow. Last-longer settlement. Deal-making (manual entry). ICM helper if time (stretch). | First full tournament can run end-to-end on staging |
| 10 | Phase 4+5 | Win-credit-to-wallet on final results. Withdrawal-request queue with two-step pattern. End-of-day reconciliation view. Begin display app at /display. | Wallet round-trip complete (deposit → spend → win → withdraw) |
| 11 | Phase 5 | Cycling display (blinds, prize pool, stats). Display polish. iPad pass on every screen. | Display polished. iPad pass report. |
| 12 | Phase 6 | Update analytics dashboard and Player App to consume new schema (including wallet read views). Backwards-compat shim. End-of-build review with Guy. | BUILD PHASE COMPLETE — feature-complete on staging |

## Build phase — Major milestones

- End of Week 1: Feature inventory + wallet design frozen. Anything added later pushes the build window.

- End of Week 3: Firestore security rules deployed to staging. HARD GATE before any production write.

- End of Week 5: First tournament can be created and run end-to-end on staging.

- End of Week 8: Every registration payment method works on staging (cash, EFTPOS, PayID, wallet, ticket).

- End of Week 9: First full tournament (registration → seating → bust-outs → payouts) runs end-to-end.

- End of Week 10: Wallet round-trip works (deposit → spend → win-credit → withdrawal request → completion).

- End of Week 12: BUILD PHASE COMPLETE. Floor App feature-complete on staging. Hand-off to Rollout phase.

## Build phase — Calendar

| Week | Dates | End-of-week deliverable |
| --- | --- | --- |
| 1 | 4 – 10 May | Feature inventory + wallet design + schema audit + ADR-001 |
| 2 | 11 – 17 May | Auth + role-aware app shell |
| 3 | 18 – 24 May | Firestore rules deployed (HARD GATE). Schema v1 frozen. Wallet ledger primitives ready. |
| 4 | 25 – 31 May | Working clock prototype |
| 5 | 1 – 7 June | Phase 2 sign-off — tournaments can be created and run end-to-end |
| 6 | 8 – 14 June | Registration with all 5 payment methods + PayID wizard live |
| 7 | 15 – 21 June | Seating + balancing + alternates working |
| 8 | 22 – 28 June | Phase 3 sign-off — full registration / seating / wallet flow |
| 9 | 29 June – 5 July | First full tournament runs end-to-end on staging |
| 10 | 6 – 12 July | Wallet round-trip complete (deposit → spend → win → withdraw) |
| 11 | 13 – 19 July | Display polished. iPad pass report. |
| 12 | 20 – 26 July | BUILD PHASE COMPLETE — feature-complete on staging |

## Rollout phase (separate schedule)

Begins once the build phase is complete. Calendar pace depends on PlayLive's tournament schedule — bug-fix cycles and parallel-run tournaments cannot be artificially compressed.

| Rollout activity | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Handbook + champion training | ██ | ██ |  |  |  |  |  |  |  |  |
| Group training |  | ██ |  |  |  |  |  |  |  |  |
| Tournaments 1–2 (parallel run) |  |  | ██ | ██ |  |  |  |  |  |  |
| Bug-fix sprint |  |  |  | ██ | ██ |  |  |  |  |  |
| Tournaments 3–5 + reconciliation |  |  |  |  | ██ | ██ | ██ | ██ |  |  |
| Pre-cutover checklist + deploy |  |  |  |  |  |  |  | ██ | ██ |  |
| Cutover + cancel Casinoware + post-mortem |  |  |  |  |  |  |  |  | ██ | ██ |

Rollout-week numbering is relative (R1, R2, ...) because absolute calendar dates depend on when the build phase completes and PlayLive's tournament schedule. Rough estimate: 8–12 weeks from build-phase completion to Casinoware switch-off.

## Rollout phase — Hard gates

- Before any production write: Firestore security rules deployed (carried over from build Week 3).

- Before parallel-run tournaments: both champions trained, handbook in hand.

- Before cutover: floor staff UAT sign-off and at least two clean end-of-day wallet reconciliations against external records.

## Slip strategy

- Build phase: critical-path tasks (clock, registration, payouts) cannot slip without pushing Week 12. Stretch goals (ICM helper, display polish beyond minimum) are the first to defer if pressure builds.

- Rollout phase: parallel run is the buffer. If issues are found, we run more parallel tournaments — cutover slips rather than rushes. Casinoware is month-to-month, so an extra month of subscription is the cost of getting cutover right.